## Sheet1
Shree Shambhubhai V. Patel College of
Computer Science & Business Management, Surat
Daily Project Work Report (TY BCA)
Group No :- |  | Project Title :- eAuto – Bike Spare Parts E-Commerce
Platform
Front-End :- React JS,HTML,CSS,JavaScript,Bootstrap 5,
AOS(Animate On Scroll),PHP (for rendering
UI and Sessions)
Back-End :- PHP (Core PHP for logic and server-side
Seat No | Name |  | processing),MySQL(Database),phpMyAdmin
423 | Dhruv Dholiya |  | (Database Management),XAMPP(Local
424 | Dharmik Dobariya |  | Development Server)
458 | Vatsal Kapadia | Project Guide :- Prof. Yesha Bheshan

## Sheet2
Sr. | Date | Module Name | Code/Design | DB Table | Doc Work | Description | URL | Sign
1 | 2025-07-15 | RG |  |  | Requirement Gathering | Started requirement gathering
2 | 2025-07-16 | RG |  |  | Requirement Gathering | Continued requirement collection
3 | 2025-07-17 | RG |  |  | Requirement Gathering | Finalized requirement points
4 | 2025-07-18 | Analysis |  |  | Website Features | Identified user/admin website features
5 | 2025-07-19 | Analysis |  |  | Website Features | Detailed system feature planning
6 | 2025-07-20 | Holiday (Sunday)
7 | 2025-07-21 | Analysis |  |  | Website Features | Finalized features for development
8 | 2025-07-22 | Analysis |  |  | Website Features | Prepared use case diagram
9 | 2025-07-23 | Template |  |  |  | Collected user interface templates
10 | 2025-07-24 | Template |  |  |  | Finalized user-side templates
11 | 2025-07-25 | Template |  |  |  | Admin-side template analysis
12 | 2025-07-26 | Template |  |  |  | Selected final templates
13 | 2025-07-27 | Holiday (Sunday)
14 | 2025-07-28 | Database Design | ✔ |  | ER Diagram | Created E-R diagram & table structure
15 | 2025-07-29 | Database Design | ✔ |  | Table Structure | Implemented users, products tables

## Sheet3
Sr. | Date | Module Name | Code/Design | DB Table | Doc Work | Description | URL | Sign
1 | 2025-07-30 | Database Design | ✔ | orders, order_items | Table Structure | Implemented orders, order_items tables
2 | 2025-07-31 | Admin Login | ✔ | admin |  | Developed admin login with session
3 | 2025-08-01 | User Registration | ✔ | users | Requirement Gathering | Signup with validation
4 | 2025-08-02 | User Login | ✔ | users | Website Features | Login + session management
5 | 2025-08-03 | Holiday (Sunday)
6 | 2025-08-04 | Admin Dashboard | ✔ | products | Website Features | Add/edit/delete product features
7 | 2025-08-05 | Product Module | ✔ | products | Website Features | User-side product listing
8 | 2025-08-06 | Cart Module | ✔ | cart |  | Cart operations (add/update/delete)
9 | 2025-08-07 | Checkout Module | ✔ | orders, order_items |  | Address & payment selection
10 | 2025-08-08 | Order Placement | ✔ | orders, order_items |  | Order placement with address/payment
11 | 2025-08-09 | User Panel | ✔ | orders, order_items |  | Profile view/edit, order tracking
12 | 2025-08-10 | Holiday (Sunday)
13 | 2025-08-11 | Order History | ✔ |  |  | List of past orders
14 | 2025-08-12 | Project Setup | ✔ |  |  | Final folder structure, file cleanup
15 | 2025-08-13 | Navbar Integration | ✔ |  | Website Features | Integrated header with cart, login

## Sheet4
Sr. | Date | Module Name | Code/Design | DB Table | Doc Work | Description | URL | Sign
1 | 2025-08-14 | Footer Integration | ✔ |  | Website Features | Added responsive footer
2 | 2025-08-15 | Route Protection | ✔ | users |  | PrivateRoute setup for admin/user routes
3 | 2025-08-16 | Image Management | ✔ | products |  | Image upload & preview with product module
4 | 2025-08-17 | Holiday (Sunday)
5 | 2025-08-18 | Brand Filtering | ✔ | products |  | Filtered products by bike brand
6 | 2025-08-19 | Responsive Design | ✔ |  |  | Completed responsive testing for all pages
7 | 2025-08-20 | Empty Cart UX | ✔ | cart |  | Styled empty cart experience
8 | 2025-08-21 | Delivery Address | ✔ | users, orders |  | Saved addresses with default checkbox
9 | 2025-08-22 | Order Success Page | ✔ | orders |  | Order placed confirmation with summary
10 | 2025-08-23 | Order Detail Page | ✔ | orders, order_items |  | View full order details
11 | 2025-08-24 | Holiday (Sunday)
12 | 2025-08-25 | UI Polish | ✔ |  |  | Final color and spacing adjustments
13 | 2025-08-26 | Post-Submission Review | ✔ |  |  | Reviewed submitted project for improvements
14 | 2025-08-27 | Documentation Update | ✔ |  | Final Report Update | Added final notes and appendix to report
15 | 2025-08-28 | Bug Fixes | ✔ | All Tables |  | Minor bug fixes after submission

## Sheet5
Sr. | Date | Module Name | Code/Design | DB Table | Doc Work | Description | URL | Sign
1 | 2025-08-29 | Code Optimization |  |  |  | Improved performance and cleaned code
2 | 2025-08-30 | Testing |  |  |  | System testing and bug fixing
3 | 2025-08-31 | Holiday (Sunday)
4 | 2025-09-01 | Testing |  |  |  | System testing and bug fixing
5 | 2025-09-02 | Final Testing |  | All Tables |  | Minor bug fixes after submission
6 | 2025-09-03 | UI Enhancements |  |  |  | Adjusted final UI elements for clarity
7 | 2025-09-04 | Project Video Update |  |  |  | Edited final project demo video
8 | 2025-09-05 | Documentation |  |  | Final Report | Completed project report
9 | 2025-09-06 | Report Formatting |  |  |  | Reformatted final report for printing
10 | 2025-09-07 | Holiday (Sunday)
11 | 2025-09-08 | Final Approval Process |  |  |  | Submitted for final review and approval
12 | 2025-09-09 | Project Completion |  |  | Completion Report | Official project closure and final documentation